Week 1, Oct 2 – Oct 6

Mon

- Forma Mob in 6am

- NW Abatement mob in 7am – Indoor boom lift staged on concrete. Set up containments starting at NE corner.

Fencing & Signage setup at logistics yard 6am – All Star Fencing, Forma signage

Forklift delivery 7am - Rental

Dumpster delivery 7am – Renu/Northstar

Open Louvers 7am – Forma (scissor lift 1day)

Stage Floor Removal 8am – Forma 1carp 1 lab 2day

- Brand Safway setup scaffolding 2nd floor and tower 8am

- Reliable Electric start Electrical Safe off and demo @NW stage wall

- Hydrotech safe off and demo sprinks

- Firetek safe off and demo Fire Alarm -

Tues

NW Abatement continue Set up containment NE corner and Mezz decks, start demo. Remove sheetrock NW and NE stage wing walls at stage level

Forma continue stage floor removal

Reliable continue safe off and demo below stage floor

Locate Sewer Tie in

Wed

NW Abatement continue demo NE corner and Mezz decks

GM Mob to site

- Shoring/demo NW stage wall

Thurs

Cascade Mob to site 7am

Cascade/GM Saw cut and demo NW area

Fri

Cascade/GM continue demo/excavate NW area

Safe off excavation area

Week 2, Oct 9 – Oct 13

Mon

GM Shoring/demo NE stage wall

NW Abatement set containment NW corner

Capital Excavate at Sewer

Week 2 continued….

Tues

Sewer Tie in

Cascade/GM demo excavate NE area

NW Abatement demo NW area

Wed

Inspect Sewer connection

Cascade/GM continue demo excavate NE area

NW Abatement continue demo NW

Thurs

- Bed and backfill sewer connection

- Cascade/GM continue Demo/excavate NE area

- NW Abatement continue demo NW

Fri

GM Start Form and tie Bar

NW Abatement continue demo NW

GM Start Form and tie bar

Week 3, Oct16 – Oct20

Mon

NW Abatement continue demo Mezz decks

GM Finish form and tie bar – inspections

Tues

NW Abatement continue demo mezz decks

GM Conc Pour day all footings

Wed

NW Abatement continue demo mezz decks

GM Strip Footings, Prep floor Infill pourbacks

Thurs

NW abatement continue demo mezz decks

GM Inspect and Conc Pour day- floor infills

Fri

Week 3 continued…

NW Abatement Clean up and demob

Brand/Safway staging demob

GM Clean up and demob equip

Week 4, Oct 23 – Oct 27

Mon.

Patch back NE walls

Patch back Stage

Tues

Patch back NW walls

Patch back Stage

Wed

Electrical Re-feed and trim

F/A tie in (If/As needed)

Fire Sprink Tie in (If/As needed)

Clean up

Thurs

Electrical Re-feed and trim

F/A tie in (If/As needed)

Fire Sprink Tie in (If/As needed)

Clean up

Friday

Clean up and Demob