**Week 1, Oct 2 – Oct 6**

Mon

* Forma Mob in 6am
* NW Abatement mob in 7am – Indoor boom lift staged on concrete. Set up containments starting at NE corner.
* Fencing & Signage setup at logistics yard 6am – All Star Fencing, Forma signage
* Forklift delivery 7am - Rental
* Dumpster delivery 7am – Renu/Northstar
* Open Louvers 7am – Forma (scissor lift 1day)
* Stage Floor Removal 8am – Forma 1carp 1 lab 2day
* Brand Safway setup scaffolding 2nd floor and tower 8am
* Reliable Electric start Electrical Safe off and demo @NW stage wall
* Hydrotech safe off and demo sprinks
* Firetek safe off and demo Fire Alarm -

Tues

* NW Abatement continue Set up containment NE corner and Mezz decks, start demo. Remove sheetrock NW and NE stage wing walls at stage level
* Forma continue stage floor removal
* Reliable continue safe off and demo below stage floor
* Locate Sewer Tie in

Wed

* NW Abatement continue demo NE corner and Mezz decks
* GM Mob to site
* Shoring/demo NW stage wall

Thurs

* Cascade Mob to site 7am
* Cascade/GM Saw cut and demo NW area

Fri

* Cascade/GM continue demo/excavate NW area
* Safe off excavation area

**Week 2, Oct 9 – Oct 13**

Mon

* GM Shoring/demo NE stage wall
* NW Abatement set containment NW corner
* Capital Excavate at Sewer

Week 2 continued….

Tues

* Sewer Tie in
* Cascade/GM demo excavate NE area
* NW Abatement demo NW area

Wed

* Inspect Sewer connection
* Cascade/GM continue demo excavate NE area
* NW Abatement continue demo NW

Thurs

* Bed and backfill sewer connection
* Cascade/GM continue Demo/excavate NE area
* NW Abatement continue demo NW

Fri

* GM Start Form and tie Bar
* NW Abatement continue demo NW
* GM Start Form and tie bar

**Week 3, Oct16 – Oct20**

Mon

* NW Abatement continue demo Mezz decks
* GM Finish form and tie bar – inspections

Tues

* NW Abatement continue demo mezz decks
* GM Conc Pour day all footings

Wed

* NW Abatement continue demo mezz decks
* GM Strip Footings, Prep floor Infill pourbacks

Thurs

* NW abatement continue demo mezz decks
* GM Inspect and Conc Pour day- floor infills

Fri

Week 3 continued…

* NW Abatement Clean up and demob
* Brand/Safway staging demob
* GM Clean up and demob equip

**Week 4, Oct 23 – Oct 27**

Mon.

* Patch back NE walls
* Patch back Stage

Tues

* Patch back NW walls
* Patch back Stage

Wed

* Electrical Re-feed and trim
* F/A tie in (If/As needed)
* Fire Sprink Tie in (If/As needed)
* Clean up

Thurs

* Electrical Re-feed and trim
* F/A tie in (If/As needed)
* Fire Sprink Tie in (If/As needed)
* Clean up

Friday

* Clean up and Demob